## OVERVIEW
Scrum Evaluation Tool
COLUMN KEY | DEFINITION
ID | Unique identifier per Scrum Guide potential implementation goal element (for easier reference).
Framework element | Short definition of the framework element to implement
Ref(erence) | Page.Paragraph reference to where the element can be found in the ScrumGuide-with-AgileManifesto.pdf
Quality | Score the coach gives during team observations for that framework element
Notes | Notes from the coach from observations, interviews, and surveys
For each tab of the tool you observe, give a score, and add notes that explain the justification for the score (problem areas or activities that denote excellence).
The score for each tab is taken at a specific moment in time. You can duplicate the sheet and add a date to the tab name to show progress over time.

## Quality Rating Scale
Score | Quality Rating | Definition
2 | Excellent | Implemented, meeting the purpose, and considered for continuous improvement
1 | Great | Implemented, and meeting the purpose
0 | Good | Implemented
-1 | Poor | Implemented in name only
-2 | Missing | Not implemented

## Scrum Team Definition
Scrum Team Definition
ID | Framework Element | Ref | Quality | Notes
1.1 | Has one PO | 5.3
1.2 | Has one Scrum Master | 5.3
1.3 | Small Team, 10 or fewer, with a goal of being nimble, and complete work in a sprint | 5.3,5.5
1.4 | Cross functional (everyone needed) | 5.4
1.5 | Self-managing (who, what, when, and how) | 5.4
1.6 | Product teams share the same product backlog, product goal, and product owner | 5.5
1.7 | Stakeholder collaboration responsibility | 5.6
1.8 | Verification responsibility | 5.6
1.9 | Collaboration responsibility | 5.6
2 | Maintenance responsibility | 5.6
2.1 | Operational responsibility | 5.6
2.2 | Experimentation responsibility | 5.6
2.3 | Research and Development responsibility | 5.6
2.4 | The org both structures and empowers the team to manage their own work | 5.6
2.5 | Organized around a sustainable and consistent sprint cadence | 5.6
2.6 | Value creation accountability | 5.7
2.7 | Useful increment per sprint accountability | 5.7

## Developer Accountabilities
Developer Accountabilities
ID | Framework Element | Ref | Quality | Notes
2.1 | Create usable increment each sprint | 6.1
2.2 | Skillset is/becomes broad and variable within work domain | 6.2
2.3 | Sprint plan creation accountability | 6.2
2.4 | Creation and adherence to the Definition of Done (DoD) accountability | 6.2
2.5 | Plan daily adaptation accountability | 6.2
2.6 | Holding each other accountable | 6.2

## Product Owner Accountabilities
Product Owner Accountabilities
ID | Framework Element | Ref | Quality | Notes
3.1 | Maximize the value of the product resulting from teamwork | 6.3
3.2 | Manages the backlog | 6.4
3.3 | Goal communication and development accountability | 6.4
3.4 | Creating and clearly communicating Product Backlog Items (PBIs) | 6.4
3.5 | Ordering (prioritization) PBIs | 6.4
3.6 | Ensuring backlog transparency, visibility, and that it is understood | 6.4
3.7 | While remaining accountable, the above activities may be delegated to others | 6.5
3.8 | Whole org must respect the decision-making power of the PO in terms of visibility of PBI content, ordering of PBIs, in review of outcomes of the inspectable increment in the Sprint Review | 6.6
3.9 | Product backlog should reflect the needs of many stakeholders | 6.7
3.10 | The PO is a single individual and not a committee | 6.7
3.11 | Changes to the backlog are the result of convincing the PO | 7.1

## Scrum Master Accountabilities
Scrum Master Accountabilities
ID | Framework Element | Ref | Quality | Notes
4.1 | Establishing Scrum as defined in the Scrum Guide | 7.2
4.2 | Train and implement the team and the org in Scrum theory and practice | 7.2
4.3 | Ensuring team effectiveness by enabling the scrum team to improve its practices within the framework | 7.3
4.4 | Embrace servant leadership model to the team (piecemeal and concurrence) | 7.4
4.5 | Coaching self-management and cross-functionality to the team | 7.4
4.6 | Coaching focus on creating high-value increments on the team | 7.4
4.7 | Coach adherence to the Definition of Done on the team | 7.4
4.8 | Causing the removal of team impediments with the team | 7.4
4.9 | Ensure positive, productive, timeboxed scrum events on the team | 7.4
4.1 | Embrace servant leadership model to the PO | 7.5
4.11 | Find techniques for defining good product goals for the PO | 7.5
4.12 | Helping the whole team understand how to embrace clear and concise PBIs | 7.5
4.13 | Help establish product planning approached that embrace empiricism in complex environments | 7.5
4.14 | Facilitate stakeholder collaboration as requested/needed | 7.5
4.16 | Embrace servant leadership model to the organization | 8.1
4.17 | Leading, training, and coaching the org in Scrum adoption | 8.1
4.18 | Planning and advising org Scrum implementations | 8.1
4.19 | Helping employees and stakeholders adopt empiricism | 8.1
4.2 | Removing barriers between stakeholders and Scrum teams | 8.1

## Scrum Event Commonalities
Scrum Event Commonalities
ID | Framework Element | Ref | Quality | Notes
5.1 | All events happen consistently within the framework of the sprint cadence (not around or outside) | 8.2
5.2 | Events center on the inspection and adaption of empiricism | 8.2
5.3 | Events are critical for enabling transparency | 8.2
5.4 | Failure to perform the event and/or in an empirical manner creates lost opportunity | 8.2
5.5 | Event regularity creates consistency and a reduction in meetings | 8.2
5.6 | Scheduling is ideally always the same time and place each sprint to reduce complexity | 8.2

## Event - Sprint
Sprint Event
ID | Framework Element | Ref | Quality | Notes
6.1 | Fixed in length, one month long or less (timeboxed and consistent) | 8.4
6.2 | New sprint starts immediately after the last one ends | 8.4
6.3 | All work necessary to achieve the product goal (Sprint planning, daily scrum, Sprint review, retrospective) happen within the Sprint | 8.5
6.4 | No changes are made that would endanger the Sprint goal | 8.6
6.5 | Quality does not decrease (built in – not a phase – no dropped) | 8.6
6.6 | Product backlog is refined as needed | 8.6
6.7 | Scope may be clarified and re-negotiated with the PO | 8.6
6.8 | Sprints create predictability via inspection and adaptation at least once per month for the Product goal | 8.7
6.9 | Sprints that are too long may introduce too much complexity or result in working on invalidated goals, creating risk | 9.1
6.10 | Shorter sprints create more empirical learning cycles and reduce risk associated with larger costs over longer periods | 9.1
6.11 | Treat short sprints like short “projects” (in terms of focus and outcome delivery) | 9.1
6.12 | Do not replace empiricism with valuable tools like burn-down, burn-up or cumulative flow (outcome vs output). | 9.2
6.13 | Only use the empiricism of the past to influence forward-looking decision-making. | 9.2
6.14 | If the sprint goal is deemed obsolete, the PO (and only the PO) can cancel the Sprint | 9.3

## Event - Sprint Planning
Sprint Planning Event
ID | Framework Element | Ref | Quality | Notes
7.1 | As a collaborative team, identify the work to be performed (which stories and any details) | 9.4
7.2 | PO is responsible to ensure the team is ready to discuss the appropriate PBIs and how they map to the Product goal (PO presents the goal, and team looks at and helps identify related stories to perform work on) | 9.5
7.3 | Answer the question: Why is this Sprint valuable? PO proposes value. Whole team defines the goal together in a manner that can be explained to stakeholders. The Goal must be established before the end of the meeting. | 9.6
7.4 | Answer the question: What can be done this Sprint? Team and PO select items from the backlog that are relevant to the goal. Additional refinement, clarification, slicing can happen to target the goal best with scope of potential work. | 9.7
7.5 | Estimation of what can be completed is based on empiricism by the team, considering their capacity, the DoD, their understanding of the work to be performed, and the goal. | 9.8
7.6 | Answer the question: How will the chosen work get done? | 10.1
7.7 | Decomposition of PBIs into work of a day or less (only the developers should decompose PBIs) Noone tells the teams how to decompose or deliver | 10.1
7.8 | The Sprint backlog is established, comprised of the Sprint Goal, the selected PBIs, and the plan for delivering them | 10.2
7.9 | The meeting should take no more than 8 hours for a 1-month Sprint (less for shorter sprints, accordingly). | 10.3

## Event - Daily Scrum
Daily Scrum Event
ID | Framework Element | Ref | Quality | Notes
8.1 | Goal of inspecting progress and adapting the Sprint Backlog (re-negotiating the goal, altering selected PBIs, updating the plan for coming work within the Sprint) with a focus on the next 24 hours of work. | 10.4
8.2 | 15-minutes for the Developers of the Scrum Team | 10.5
8.3 | Same time and place every day, to reduce complexity | 10.5
8.4 | If the PO and SMs are literally actively team Developers (materially contributing to the deliverable of the sprint) then they participate as developers | 10.5
8.5 | The Developers decide how to orchestrate the daily scrum so long as they achieve the goal (8.1) | 10.6
8.6 | Team actively improves communication, identify impediments, promote quick decision-making, eliminate the need for other meetings. | 10.7
8.7 | It is expected that teams meet outside of the daily Scrum for more detailed specific discussion planned for the next 24 hours of work. | 10.8

## Event - Sprint Review
Sprint Review Event
ID | Framework Element | Ref | Quality | Notes
9.1 | Goal of inspecting the delivered outcome to determine future adaptations. | 10.9
9.2 | Scrum team presents the outcome of their work to key stakeholders | 11.1
9.3 | Team presents accomplishments along with changes (new discoveries, uncompleted outcomes, other applicable environmental factors) | 11.2
9.4 | Product Backlog may be updated based on discussion to add new opportunities or re-prioritize PBIs | 11.2
9.5 | Treated as a working session and not a presentation | 11.2
9.6 | 2nd to last event in the Sprint lasting a max of 4 hours for a month-long Sprint (less if the sprint is shorter) | 11.3

## Event - Sprint Retro
Sprint Retrospective Event
ID | Framework Element | Ref | Quality | Notes
10.1 | Goal of inspecting and adapting team quality and effectiveness | 11.4
10.2 | Team discusses individuals, interactions, processes, tools and their DoD. | 11.5
10.3 | Identify assumptions that lead the team toward reduced quality or effectiveness | 11.5
10.4 | Answer the question: What went well in the Sprint? | 11.5
10.5 | Answer the question: What problems were encountered? | 11.5
10.6 | Answer the question: How did we solve our problems? Which were not solved? | 11.5
10.7 | Team identifies changes to be made | 11.6
10.8 | The most impactful changes are identified | 11.6
10.9 | They (10.8) may even be added to the backlog for the next sprint | 11.6
10.10 | The Sprint Retrospective is the last event of the Sprint timebox. | 11.7

## Artifact - Commonalities
Scrum Artifact Commonalities
ID | Framework Element | Ref | Quality | Notes
11.1 | All artifacts represent work or value | 11.8
11.2 | Goal of maximizing transparency of key information | 11.8
11.3 | Everyone who inspects artifacts has the same basis for adaptation | 11.8
11.4 | Each artifact is committed to provide information that enhances transparency in a manner that make outcome progress measurable | 12.1
11.5 | Each artifact is committed to provide information that is focused in a manner that make outcome progress measurable | 12.1
11.6 | Standard: The Product Goal makes Product Backlog transparent and focused and measurable | 12.1
11.7 | Standard: The Sprint Goal makes the Sprint Backlog transparent and focused and measurable | 12.1
11.8 | Standard: The DoD makes the delivered increment of outcome transparent and focused and measurable | 12.1
11.9 | Commitment to these standards reinforces empiricism and Scrum values for teams and stakeholders | 12.2

## Artifact - Prod Backlog
Product Backlog Scrum Artifact
ID | Framework Element | Ref | Quality | Notes
12.1 | An emergent artifact (grows, changes, prioritizes) of what is needed for the improvement of a product | 12.3
12.2 | The single source of work undertaken by the Scrum team | 12.3
12.3 | PBIs able to be “Done” in a single sprint can be selected for Sprint Planning | 12.4
12.4 | PBIs achieve a level of transparency permitting them for a Sprint (12.3) after team refining activities (plural) | 12.4
12.5 | PRODUCT BACKLOG REFINEMENT is the act of breaking down and further defining a PBI into smaller more precise outcomes containing more detailed attributes like description, order, and size. | 12.4
12.6 | Scrum Team Developers doing the work are responsible for sizing | 12.5
12.7 | POs may influence developers through information sharing and reviewing trade-offs | 12.5
12.8 | The backlog is committed to achieving a future state for the product (the product goal), and teams plan sprints around a targeted product goal. | 12.6
12.9 | Product Definition: A Product has clear boundaries, known stakeholders, well-defined users/customers, and is a vehicle to deliver value. It can be a physical product, a service, or something more abstract. | 12.7
12.10 | Achieving the Product Goal is the long-term objective for a Scrum Team. They fulfill (or abandon) a goal before moving on to the next). Sprint goals are the increment that contributes to the next product goal. | 12.8

## Artifact - Sprint Backlog
Sprint Backlog Srum Artifact
ID | Framework Element | Ref | Quality | Notes
13.1 | Contains the Sprint Goal (the Why) | 13.1
13.2 | Contains a list of PBIs (the What) | 13.1
13.3 | Contains an actionable plan for delivering the increment (the How) | 13.1
13.4 | By and for the developers | 13.2
13.5 | Highly visible, real-time picture of the work for the Sprint to achieve the Sprint goal | 13.2
13.6 | The Sprint backlog is updated throughout the sprint as more is learned | 13.2
13.7 | Enough detail in the plan to inspect and adapt the plan daily | 13.2
13.8 | The Sprint backlog is committed to achieving the Sprint Goal | 13.3
13.9 | Sprint goal is the single objective of a team sprint | 13.3
13.10 | Sprint goal creates natural flexibility in terms of the work planned (subject to inspection and adaptation) | 13.3
13.11 | Sprint goal creates coherence and focus – encouraging the team to work together rather than on separate allocated initiatives/work (ensures everyone is contributing to the top priority rather than simply something – outcome over output) | 13.3
13.12 | Sprint goal is created during Sprint Planning as a key backlog element | 13.4
13.13 | All work by developers should keep the Sprint goal in mind | 13.4
13.14 | If the work turns out to be different from what they expected, they work with the PO to negotiate the scope within the Sprint backlog without affecting the Sprint Goal | 13.4

## Artifact - Increment
Scrum Increment Artifact
ID | Framework Element | Ref | Quality | Notes
14.1 | The increment is a concrete steppingstone toward the Product Goal (A Sprint attempts to deliver an increment aligned with a Sprint Goal, that is a stepping stone toward achieving a Product Goal). | 13.5
14.2 | Increments and integrated with and verified with all previous increments of a Product Goal. Increments must be usable. | 13.5
14.3 | A Sprint increment can be “delivered” to stakeholders as soon as possible and not wait for the end of the Sprint. | 13.6
14.4 | A Sprint may deliver multiple increments. The sum of all Sprint increments is inspected at the Sprint review empirically, so that the future progress of the Product Goal can be adapted. | 13.6
14.5 | The Sprint Review is never to be a gate for the release of an increment. | 13.6
14.6 | Work cannot be considered part of an increment unless it meets the DoD. | 13.7
14.7 | The Increment is committed to achieving the Definition of Done | 14.1
14.8 | The DoD is a formal description of the quality measures met by the increment of the product. | 14.1
14.9 | The completion of the first PBI in terms of meeting the DoD is the start of an increment | 14.2
14.10 | DoD creates transparency for completion | 14.3
14.11 | If a PBI does not meet the DoD, it is not presented at the Sprint Review (it may be explained that it was not completed, but it is not partially presented for inspection and product goal adaptation). It does not automatically go into the next Sprint. Its default state is to return to the backlog and be considered by the PO and Team in terms of prioritization for future sprints. | 14.3
14.12 | If there is an organizational DoD, the team must include the Org DoD as a baseline for the team’s DoD. Otherwise, the team creates an appropriate DoD for the specific product. | 14.4
14.13 | Developers conform to the DoD. All teams working on the same product share a DoD. | 14.5